## grantchart
grantchart
split tasks week by week display date system and target time of board
10/01/2023 to 13/01/2023
Name | Subitems | Person | Status | Date | Item ID (auto generated)
resarch stuff to do in nottingham |  | liam | Done | 2023-01-27 | 1143881147
plan and write popostals ideas (4) |  | liam | Done | 2023-01-12 | 1143881150
survey |  | liam | Done | 2023-01-14 | 1143881153
moodboard |  | liam | Done | 2023-01-15 | 1144216595
resarch more in to heigh maps for unreal engine |  | liam | Done | 2023-01-15 | 1144218445
2023-01-12 to 2023-01-27
Next week 17/01/2023 to 19/01/2023
Name | Subitems | Person | Status | Date | Item ID (auto generated)
feedback on idea |  | liam | Done | 2023-01-20 | 1143895815
finalise the plan |  | liam | Working on it | 2023-01-20 | 1143896431
update risk assetsment |  | liam | Done | 2023-01-20 | 1144218817
survey 2.0 will be out next narrow down |  | liam | Done | 2023-01-20 | 1144458920
research on existed products in games |  | liam | Done | 2023-01-25 | 1145839364
2023-01-20 to 2023-01-25
24/01/2023 - 27/01/2023
Name | Subitems | Person | Status | Date | Item ID (auto generated)
assets |  | liam | Done | 2023-01-27 | 1145838887
survay 3 of fonts and colours |  | liam | Working on it | 2023-01-27 | 1145839066
update risk assements |  | liam | Working on it | 2023-01-26 | 1145839098
reseach high maps |  | liam | Working on it | 2023-01-26 | 1145839432
finshed any last minint research |  | liam | Working on it | 2023-01-31 | 1145839038
2023-01-26 to 2023-01-31
suggest feedback needs doing
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Quite basic, add some more detail |  |  | Stuck | 2023-01-31 | 1147507780
Graphs need titles, so we know what they are. |  |  | Working on it | 2023-01-31 | 1147507807
Explanation of why the escape room information important, analyse the graphs, why does some being more trending than others matter? |  |  | Stuck | 2023-01-31 | 1147507822
Same with Arkham Knight- explain how you might use that information in your game development. |  |  | Done | 2023-01-31 | 1147507931
See explanation of why you are doing client feedback. Why have you asked the questions in your survey? What did you learn from each question in your survey. |  |  | Stuck | 2023-01-31 | 1147507939
Include pictures of the trello week by week, need to see the progress |  |  | Working on it | 2023-01-31 | 1147507954
Do weekly evaluations of how it is going and how much you've done. |  |  | Working on it | 2023-01-31 | 1147507967
Need a more justification for why choosing idea 4 over idea 3, explain that they were even in the survey and that's why you have chosen it. |  |  | Done | 2023-01-31 | 1147507979
Need to see a prototype |  |  | Done | 2023-01-31 | 1147507985
2023-01-31
production week
Name | Subitems | Person | Status | Date | Item ID (auto generated)
setup risk asseement |  | liam | Done | 2023-01-31 | 1146148877
setup github |  | liam | Done | 2023-01-31 | 1146148878
do all sigins for each stop |  | liam | not started yet | 2023-01-31 | 1146148885
plan rotute to each stop |  | liam | not started yet | 2023-01-31 | 1146148906
props |  | liam | not started yet | 2023-01-31 | 1145838892
list the facts make sure spell and grammar is correct facts to displayed |  | liam | not started yet | 2023-01-31 | 1146148950
2023-01-31

## grantchart-updates
grantchart | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
1143881147 | resarch stuff to do in nottingham | Update |  | liam | 11/January/2023 10:08:37 AM | ﻿research ﻿ | 0 |  | 20696600
1143895815 | feedback on idea | Update |  | liam | 12/January/2023 11:12:20 AM | ﻿narrow down idea to 1 ﻿plan it out on monday.com as gantchart and plan smaller on trello | 0 |  | 21003060
1144216595 | moodboard | Update |  | liam | 12/January/2023 11:13:09 AM | ﻿on all ideas docoment them on my website ﻿ | 0 |  | 21003102
1144458920 | survey 2.0 will be out next narrow down | Update |  | liam | 16/January/2023 05:48:34 PM | ﻿going prep this tormrow ﻿ | 0 |  | 21433267
1146148950 | list the facts make sure spell and grammar is correct facts to displayed | Update |  | liam | 22/January/2023 10:32:57 PM | list the facts make sure spell and grammar is correct facts to displayed | 0 |  | 22269300
1147507822 | Explanation of why the escape room information important, analyse the graphs, why does some being more trending than others matter? | Update |  | liam | 27/January/2023 01:18:32 PM | Need to explain what does that research mean to you | 0 |  | 23284888