## gant-chart
Gant chart
split tasks week by week display date system and target time of board
10/01/2023 to 13/01/2023
Name | Subitems | Person | Status | Date | Item ID (auto generated)
resarch stuff to do in nottingham |  | liam | Done | 2023-01-27 | 1143881147
plan and write popostals ideas (4) |  | liam | Done | 2023-01-12 | 1143881150
survey |  | liam | Done | 2023-01-14 | 1143881153
moodboard |  | liam | Done | 2023-01-15 | 1144216595
resarch more in to heigh maps for unreal engine |  | liam | Done | 2023-01-15 | 1144218445
2023-01-12 to 2023-01-27
Next week 17/01/2023 to 19/01/2023
Name | Subitems | Person | Status | Date | Item ID (auto generated)
feedback on idea |  | liam | Done | 2023-01-20 | 1143895815
finalise the plan |  | liam | Done | 2023-01-20 | 1143896431
update risk assetsment |  | liam | Done | 2023-01-20 | 1144218817
survey 2.0 will be out next narrow down |  | liam | Done | 2023-01-20 | 1144458920
research on existed products in games |  | liam | Done | 2023-01-25 | 1145839364
2023-01-20 to 2023-01-25
24/01/2023 - 27/01/2023
Name | Subitems | Person | Status | Date | Item ID (auto generated)
assets |  | liam | Done | 2023-01-27 | 1145838887
update risk assements |  | liam | Done | 2023-01-26 | 1145839098
finshed any last minint research |  | liam | Done | 2023-01-31 | 1145839038
2023-01-26 to 2023-01-31
suggest feedback needs doing
Name | Subitems | Person | Status | Date | Item ID (auto generated)
Quite basic, add some more detail |  |  | nearly done | 2023-01-31 | 1147507780
Graphs need titles, so we know what they are. |  |  | nearly done | 2023-01-31 | 1147507807
Explanation of why the escape room information important, analyse the graphs, why does some being more trending than others matter? |  |  | Done | 2023-01-31 | 1147507822
Same with Arkham Knight- explain how you might use that information in your game development. |  |  | Done | 2023-01-31 | 1147507931
See explanation of why you are doing client feedback. Why have you asked the questions in your survey? What did you learn from each question in your survey. |  |  | Done | 2023-01-31 | 1147507939
Include pictures of the trello week by week, need to see the progress |  |  | Done | 2023-01-31 | 1147507954
Do weekly evaluations of how it is going and how much you've done. |  |  | nearly done | 2023-01-31 | 1147507967
Need a more justification for why choosing idea 4 over idea 3, explain that they were even in the survey and that's why you have chosen it. |  |  | Done | 2023-01-31 | 1147507979
Need to see a prototype |  |  | Done | 2023-01-31 | 1147507985
2023-01-31
production week
Name | Subitems | Person | Status | Date | Item ID (auto generated)
survay 3 of fonts and colours |  | liam | not started yet | 2023-01-27 | 1145839066
setup risk asseement |  | liam | Done | 2023-01-31 | 1146148877
setup github |  | liam | Done | 2023-01-31 | 1146148878
do all sigins for each stop |  | liam | Working on it | 2023-01-31 | 1146148885
plan rotute to each stop |  | liam | Working on it | 2023-01-31 | 1146148906
sigins for each stop |  | liam | Working on it | 2023-01-31 | 1145838892
list the facts make sure spell and grammar is correct facts to displayed |  | liam | Working on it | 2023-01-31 | 1146148950
feedback of prototype and reflect on it | I like the idea but you could make the tram move slower, getting in tram, Make it stop at the tramstop and maybe make it slower, make stops for tam to stop at, add 2 more tram stops, tram stops desgin, fixed sigins |  | Working on it | 2023-02-03 | 1148313871
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| I like the idea but you could make the tram move slower |  | Working on it | 2023-02-07 | 1148314119
| getting in tram |  | Working on it | 2023-02-05 | 1148314348
| Make it stop at the tramstop and maybe make it slower |  | Working on it | 2023-02-05 | 1148363320
| make stops for tam to stop at |  | Working on it | 2023-02-05 | 1148370301
| add 2 more tram stops |  | coming soon |  | 1149457587
| tram stops desgin |  | coming soon |  | 1149474908
| fixed sigins |  | Done | 2023-02-02 | 1149475847
2023-01-27 to 2023-02-03

## gant-chart-updates
Gant chart | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
1143881147 | resarch stuff to do in nottingham | Update |  | liam | 11/January/2023 10:08:37 AM | ﻿research ﻿ | 0 |  | 20696600
1143895815 | feedback on idea | Update |  | liam | 12/January/2023 11:12:20 AM | ﻿narrow down idea to 1 ﻿plan it out on monday.com as gantchart and plan smaller on trello | 0 |  | 21003060
1144216595 | moodboard | Update |  | liam | 12/January/2023 11:13:09 AM | ﻿on all ideas docoment them on my website ﻿ | 0 |  | 21003102
1144458920 | survey 2.0 will be out next narrow down | Update |  | liam | 16/January/2023 05:48:34 PM | ﻿going prep this tormrow ﻿ | 0 |  | 21433267
1146148950 | list the facts make sure spell and grammar is correct facts to displayed | Update |  | liam | 22/January/2023 10:32:57 PM | list the facts make sure spell and grammar is correct facts to displayed | 0 |  | 22269300
1147507822 | Explanation of why the escape room information important, analyse the graphs, why does some being more trending than others matter? | Update |  | liam | 27/January/2023 01:18:32 PM | Need to explain what does that research mean to you | 0 |  | 23284888